## Slide 1: Regional Consultation Community Action for Health
State presentation
Himachal Pradesh
Date 10 February, 2016

## Slide 2: ASHA
ASHAs selection process started in 2007 but later aborted
Selection process restarted in 2014 and 7752 ASHAs selected .
Induction training in module 1-5 imparted.
ASHAs started functioning in April 2015 and about 5Cr incentives disbursed till December 2015
Training in Module 6&7 Planned:
  The State TOT completed.
  District and Block training for two districts ( Kullu & Kinnaur) completed. Rest of districts is planned by March 2016.

## Slide 3: Quality of training
State Health commission has recommended to ensure the training quality.
State designed a training quality assessment tool. The training in round 6&7 is to be assessed through internal and external assessment of the training.
Internal Assessment: by the state and district officials
External assessment : External assessment by _ IPEGlobal and other developmental partners.

## Slide 4: Plans
Support Structure:
The ASHA facilitators are being planned for the state from the existing ASHAs. The State has proposed 400 ASHA Facilitators in the PIP 2016-17.
ASHA Soft:
State proposes to adopt the ASHA soft in similar lines to Karnataka and Rajasthan.
Earlier we studied Orissa model but couldn't implement it for problems in PFMS

## Slide 5: VHSNC
The state has 3243 VHSNCs constituted at the Gram Panchayat levels and presently FHW is the Member secretary.
Issues regarding optimum performance was raised :
Survey was conducted by the Community processes unit of H.P in year 2015.
Reasons that came up :
The untied grant of Rs 10000 being disbursed through the Department of Rural development Govt. of H.P
  Lack of accountability and ownership.
Need for the training of the VHSNC members in the state.

## Slide 6: Resolution of issues
Fund transfer:
Government has in principle agreed to disburse funds through Health Department
  Increasing the ownership and accountability
Training:
State had proposed the training of VHSNC members in HPDs (4) in year 2015-16 and four more districts Kangra, Shimla, Sirmour and Solan have been proposed in year 2016-17

## Slide 7: Rogi kalyan Samittees(RKS)
State has 657 Registered RKS in the Health institutions of Himachal Pradesh involved in the planning for the institutions.
The Governing body and Executive bodies are as per the G.O.I norms.
They are generating income through user charges for lab services etc.
Recruiting human resource and supporting the institutions in the purchase of equipments and drugs in the districts

## Slide 8: thanks